## Slide 1: Workshop on Procurement Requirement and Arrangements Wednesday, 17th February 2021, 11:00 AM – 1:00 PM
SKILLS STRENTHENING FOR INDUSTRIAL VALUE EHANCEMENT (STRIVE)

## Slide 2: Index
Legal aspects of STRIVE
Operational Aspects of STRIVE
Procurement Aspects of STRIVE
Procuring Entities and applicable Procurement Methods/Rules
Procurement Responsibilities of SPIU
Program Action Plan Related to Procurement
Disclosure of Procurement Information
Complaint Redressal Mechanism pertaining to Procurement of Goods, Works and Services
Procurement Reporting requirements
Procurement Audit by Auditors and World Bank

## Slide 3: Legal Aspects
Through the Program’s Legal Documents, India (as recipient of IDA credit) is formally and fully committed to ensuring that :
The Program’s results are not affected by fraud or corruption;
The Program is legally bound to be implemented as per the World Bank’s Anti Corruption Guidelines;
The Program legally complies with a set of priority actions for institutional strengthening, namely, the ‘Program Action Plan’ (PAP); and
The Program activities exclude ‘Program Exclusion Activities’

## Slide 4: Legal Aspects
It may be noted that :
The Anti-Corruption Guidelines cover all Program expenditures under STRIVE, i.e., under Results Areas 1 through 4 and under the Technical Assistance Component.
Program exclusion activities are those that :
are likely to have significant adverse impacts that are sensitive, diverse, or unprecedented on the environment and/or affected people; or
involve the procurement of:
works, estimated to cost seventy-five million United States Dollar (USD 75,000,000) equivalent or more per contract;
goods, estimated to cost fifty million United States Dollar (USD 50,000,000) equivalent or more per contract;
non-consulting services, estimated to cost fifty million United States Dollar (USD 50,000,000) equivalent or more per contract; or
consultants' services, estimated to cost twenty million United States Dollar (USD 20,000,000) equivalent or more per contract

## Slide 5: Operational Aspects of STRIVE
Operational Manual (OM) is defined in the Legal Agreement of STRIVE, which makes implementation of the Program in accordance with provisions of the OM legally binding.
Legal requirements of STRIVE are cascaded and reflected in the Operational Manual so as to ‘operationalize’ implementation in accordance with agreed arrangements.
Operational Manual (OM) of the STRIVE was prepared by DGT, MSDE on 3rd January, 2019.
OM is disclosed on DGT website whose link is https://dgt.gov.in/sites/default/files/NSC%20Approved_STRIVE_OperationsManual_v1.0.pdf

## Slide 6: Procurement Aspects of STRIVE
Objective of this section is to provide information on procurement aspects of STRIVE as detailed in the Procurement Chapter of the Operations Manual, as below :
  Applicable procurement rules
  Program Action Plan related to Procurement : ‘Procurement PAP’, as below :
  requirement of preparation of procurement plans in a standardized format and their disclosure in public domain, and their measurement; and
  importance of disclosing procurement complaint handling protocol applicable to STRIVE, and process and procedure for handling procurement related complaints in an unbiased and transparent manner

## Slide 7: Procurement Aspects of STRIVE
  Procurement disclosure requirements;
  Procurement record keeping for Program Audit; and
  Important standard terms and conditions of bidding:
  Fraud and Corruption
  Arbitration and Dispute Resolution
  Law Governing the Contract
  Insurance
  Patent Rights
  Force Majeure
  Conflict of Interest
  Payment Terms

## Slide 8: Procuring Entities and Applicable Procurement Methods/Rules
Procuring entities in STRIVE belong to both public and private sectors, as below :
  National Project Implementation Unit (NPIU)
  Central Staff Training and Research Institute (CSTARI)
  National Skill Training Institutes (NSTIs)
  National Instructional Media Institute (NIMI)
  State Project Implementation Unit (SPIU)
  State Apprentice Monitoring Cell (SAMC)
  Government and Private ITIs
  Industry Clusters (ICs)

## Slide 9: Procuring Entities and Applicable Procurement Methods/Rules
STRIVE COMPONENTS |  | Procuring Entity | Applicable Procurement Rules
PROGRAM [COVERING RESULT AREAS 1 TO 4] |  | Centrally Financed Institutions (CFIs) | GFR 2017, as updated from time to time
 |  | SPIUS, and Government ITIs | State Financial Rules/legislation on procurement, as updated from time to time
 |  | Private ITIs and ICs | Applicable procurement method to be governed by “Canons of Financial Propriety” with due attention to economy and efficiency
TECHNICAL ASSISTANCE (TA) |  | NPIU | World Bank Procurement Rules

## Slide 10: Procurement Responsibilities of SPIU
In accordance with Annexure 2 of the Operations Manual, Procurement responsibilities of the SPIU include :
    Ensuring full knowledge and systematic application, including key staff of relevant State/UT officials, of the procurement and consultancy guidelines as per Section 4.2 of STRIVE Operation Manual, for application to the technical assistance component
    Managing the procurement of works, goods and consultancies required for State/UT level activities under the project and manage the procurement of consultancies
    Preparation of Procurement Plan at the State level. In case where ITI prepares procurement Plan, the Procurement officer would ensure training at the ITI level
    Executing National Competitive Biddings
    Liaising with the Procurement Officer at the national level, providing information on issues (problems and solutions)
    Acting as a support and reference person for all project-related procurement tasks
    Submitting quarterly procurement progress reports to the SPIU Director
    Acting as first line of contact for dealing with enquiries and complaints regarding procurement referred to the SPIU [also refer to Grievance Redressal Mechanism]

## Slide 11: Program Action Plan Related to Procurement : Procurement PAP

## Slide 12: Program Action Plan Related to Procurement : Procurement PAP
Publication of Procurement Plans was followed in the earlier Vocational Training Improvement Project [VTIP]
Standardized Procurement Plan Formats: (https://dgt.gov.in/sites/default/files/IndicativePPFormat-Sample.pdf,https://dgt.gov.in/sites/default/files/IndicativePP_Format.pdf,https://dgt.gov.in/sites/default/files/PPFormat_IC.pdf ) is available at NPIU Website.
NPIU seeks feedback on, and shall be monitoring on a quarterly basis [submission of first report on March 31, 2021 :
Where we are with regard to implementation of Procurement PAP ?
Who will implement Procurement PAP ?/How/Where will this be disclosed ?/When ?
How long do we need to complete these 2 PAPs related to procurement ?
It may be noted that Contract Award Notices [to be disclosed] will have a reference to Procurement Plan

## Slide 13: Procurement Plan
Procurement Plan
lists procurement requirements, aligned with STRIVE activities in a specified format
establishes the timelines for carrying out each step in the procurement process up to contract award and the fulfillment of the requirement
allows for the monitoring of the procuring process to determine how actual performance compares with planned activities, and thus to alert the pertinent departments and adjust the procurement plan accordingly
enhances the transparency and predictability of the procurement process
gives predictability to procurement
Rule 142 of GFR, 2017 : requires the of preparation of Annual Procurement Plan and its disclosure, by all Ministries/Departments
Procurements under STRIVE shall be initiated after approval of the procurement plan from authorities as specified in the guidelines as per Section 4.2.5 of STRIVE OM

## Slide 14: Procurement Plan
All procurement plans shall need to be disclosed in public domain in a legible form by the respective procuring and implementing entities.
Copy of procurement plan and compliance with disclosure requirements shall be provided by procuring entities to Program Auditors
Procurement plan is also required to ensure that the procurement of goods conform to National Skills Qualifications Framework (NSQF) compliant courses/Standard National Council for Vocational Training (NCVT) list of Machinery/Equipment/Tools and duly approved by Institute Management Committee (IMC) (or equivalent) of respective Government/Private ITI
Any exception to this may be properly justified and approval of SPIU may be obtained before its initiation of procurement activities with regard to above exceptions. Exceptions shall be made available to Program Auditors

## Slide 15: Disclosure of Procurement Information
The following documents shall be disclosed on the website of procuring entities and on the websites of both the State Directorates and NPIU:
Approved procurement plans and their updates
Invitation for bids for goods, works, services (consulting and non-consulting) for all National Competitive Bidding (Open Tendering)
Shortlists of Consultants
Contract Award Notices [CAN] of all procurement carried out under STRIVE in standardized formats available at :(https://dgt.gov.in/sites/default/files/CANCompselection.pdf,https://dgt.gov.in/sites/default/files/CAN-DirectSelection.pdf , https://dgt.gov.in/sites/default/files/CANRFQ.pdf )
Action taken report on procurement complaints received on quarterly basis

## Slide 16: Procurement Complaint Redressal Mechanism
This was also used in predecessor Vocational Training Improvement Project [VTIP]
Procurement Complaint Redressal mechanism shall be integrated with Grievance Redressal Mechanism of STRIVE
Procurement related complaints will need to be handled with utmost confidentiality, in a fair and unbiased manner, and within stipulated timelines
All procurement related complaints shall be acknowledged in writing promptly, and a resolution provided through a written response thereafter, within stipulated timelines
In responding to any procurement related complaint, procuring entities under STRIVE have an obligation to maintain the confidentiality of the procurement process and of proprietary information provided by the complainant as part of its bid or otherwise

## Slide 17: Procurement Complaint Redressal Mechanism
All such complaints shall be handled in accordance with the protocol disclosed in the GRM note available at DGT website at :https://dgt.gov.in/sites/default/files/GuidanceNote-GRM.pdf
STRIVE Grievance Form can be seen at DGT Website at: https://docs.google.com/forms/d/e/1FAIpQLSceI6kkgAIo0kEQtvnosv-A45FPfRQN8EGkz-FUt2ZYgbGS3Q/viewform
The mechanism shall apply to all levels of implementation the Central/State/ITI and IMC levels and immediate action will be initiated on receipt of complaints from the contractors/suppliers/consultants/service providers, to redress the complaint
All complaints shall be monitored and disclosed on a quarterly basis in a standardized format (https://dgt.gov.in/sites/default/files/Complainttrackingdisclosureformat-Sample.pdf, https://dgt.gov.in/sites/default/files/Complainttrackingdisclosureformat.pdf) by Concerned Implementing agencies
These complaints will be discussed with National Project Coordinator STRIVE at DGT level and/or at the State/SPIU level with the State Project Director STRIVE list of complaints/action taken/time taken for resolution etc., shall be disclosed on NPIU/SPIU website in a standardized format

## Slide 18: Complaint Redressal Mechanism pertaining to Procurement of Goods, Works and Services
All complaints alleging Fraud and Corruption, shall be dealt with as per Central Vigilance Commission (CVC) guidelines and also be reported to the Office of the Institutional Integrity (INT) (www.worldbank.org/integrity). It may be noted that when allegations of fraud and corruption are substantiated, firms/individuals involved in misconduct are sanctioned from engaging in any new Bank-financed activity
List of debarred firms is available at URL : https://www.worldbank.org/en/projects-operations/procurement/debarred-firms

## Slide 19: Procurement Reporting requirements
The NPIU will periodically monitor the progress of implementation of the project including procurement implementation. To this effect, it will capture key procurement parameters, including implementation and achievement of procurement and PAP related to procurement at the central and state levels
Procurement reporting format [that includes Procurement PAP] is available at (https://dgt.gov.in/sites/default/files/PAPReportingFormat-Sample_0.pdf, https://dgt.gov.in/sites/default/files/PAPReportingFormat_0.pdf)
The States have to disclose all the below required information on their website quarterly basis:
    Excel format related to procurement (https://dgt.gov.in/sites/default/files/Procurement%20Data%20Format.pdf) (https://dgt.gov.in/sites/default/files/StateCFIProcurementDatasheet.pdf )

## Slide 20: Procurement Audit by Auditors : Included in Program Audit
ToRs for Internal Audit is available at https://dgt.gov.in/sites/default/files/TOR_InternalAudit.pdf
ToRs for External Audit is available at https://dgt.gov.in/sites/default/files/TOR_ExternalAudit.pdf
As per the ToRs, procurement is part of Program Audit
The procuring entities will maintain all the records of procurement exclusion activities, issue, receipt, opening, evaluation of tenders, award of contracts, payments made, complaints, and all other procurement records in chronological order and the files kept in a safe and identified place
Records should be maintained for a minimum period of 5 (five) years beyond the closure of the STRIVE project

## Slide 21: Procurement Audit by Auditors : Included in Program Audit
Auditors shall primarily report on the following :
  Goods and services financed have been procured in accordance with the relevant financing agreement and procurement norms as laid out in the operational manual
  Contracts of values higher than the stipulated thresholds have been excluded from Program Expenditure
  Whether contract award notice has been displayed in public domain. If yes, URL may be included
  Whether Annual Procurement Plan has been published. Details/URL may be provided
  Whether any complaint has been received under the Program and if yes, whether resolved. Detailed list may be included.
  Compliance with the Program Action Plan related to Procurement
  Whether any contract is issued to a firm sanctioned/debarred by the Bank

## Slide 22
Thank You