## Indicative PP Format
Format for submission of Indicative Annual procurement plan [STRIVE]
Name of State : Uttarakhand
Annual Procurement Plan for Financial Year : |  |  |  | 2020-21 and 2021-22
Date of Approval of Annual Procurement Plan : |  |  |  | 31-07-2020 & 03-02-2021
Approved By/Name of Approving Authority : |  |  |  | State Stareeing Authority(SSC)
S. No. | Procurement Category | Full Name of Procuring Entity (SPIU/ ITI/ SMAC/ IC) | Name/Description of Procurement/Selection | Estimated Cost [INR] | Results Area | Procurement Mode | Applicable Procurement Rules | Use of GEM [Yes/No] | Use of eProcurement [Yes/No] | Procurement Method | Market Approach [National/ International] | Proposed Procurement Start Date | Pre-bid Conference Date [if any] | Proposed Procurement End Date | Tentative Contract Award Date | Tentative Contract Duration [Months] | Tentative Completion Date | Remarks
[1] | [2] | [3] | [4] | [5] | [6] | [7] | [8] | [9] | [10] | [11] | [12] | [13] | [14] | [15] | [16] | [17] | [18] | [19]
1 | consultancy services | SPIU Uttarakhand | Website design https://dsde.uk.gov.in/ | 250000 | RA 2 | Public Procurement | State Financial Rule | No | No | Quotation | National | _ |  | _ | 2020-07-13 |  | 2021-03-01 | work completed
2 | NoN consultancy services | SPIU Uttarakhand | SWAN Internet connectivity in 21 ITIs through ITDA | 48,06,928.00 | RA 2 | Public Procurement | State Financial Rule | No | Yes | Through State Govt. approved agencey ITDA Dehradun | National | 2021-06-29 |  | 2021-12-18 | 2021-12-25 | 3 | 2022-03-26 | Delayed due to covid-19 and E- tender floated but sufficient proposal not received.Retendering process start again by ITDA.
3 | Civil and Electrical Maintanance work | SPIU Uttarakhand | Civil & Electrical Maintance work of Hostel in 03 Govt ITIs for OJT | 6667000 | RA 2 | Public Procurement | State Financial Rule | No | No | Through State Govt. approved construction agencey | National | 2021-12-15 |  | 2021-12-31 | 2021-12-31 | 3 | 2022-03-29
4 | NoN consultancy services | SPIU Uttarakhand | SWAN Internet connectivity in ITIs through ITDA | 71,93,072.00 | RA 2 | Public Procurement | State Financial Rule | No | No | Through State Govt. approved agencey ITDA Dehradun | National | 2022-01-15 |  | 2021-01-29 | 2022-02-14 | 4 | 2022-06-15
5 | Goods | SPIU Uttarakhand | Smart classroom establish in GITI | 50,00,000.00 | RA 2 | Public Procurement | State Financial Rule | Yes | Yes | E- Proucrement/GeM | National | 2021-12-28 |  | 2022-01-17 | 2022-02-07 | 1 | 2022-03-05
6 | Goods | SPIU Uttarakhand | Purchase of furniture for Hostel that furniture will be use for Trainees which will come for OJT | 25,00,000.00 | RA 2 | Public Procurement | State Financial Rule | Yes | No | Open Bidding | National | 2022-04-08 | 2022-04-28 | 2022-05-25 | 2022-06-15 | 1 | 2022-07-14 | After complitaton of civil/ maintainance work of 03 GITIs Hostel procurement will be started
7 | NoN consultancy services | SPIU Uttarakhand | Tracer study | 4400000 | RA 2 | Public Procurement | State Financial Rule | No | Yes | Open Bidding | National | 2021-12-25 | 2022-01-02 | 2022-02-01 | 2022-02-03 | 2 | 2022-03-31
Annual Procurement Plan may be prepared on the assumption that total budget will be released
Procuring entities shall ensure that procurements are carried out as per Delegation of Financial Powers and within Categories defined as 'Eligible Expenditure' in the Operations Manual
Specifications for goods to be procured shall be as per approved specifications for that trade, approved by the Competent Authority
Note on B8: ====== ID#AAAARN0BJ-8 tc={46DB74E6-C043-4A5F-BC76-8AAD1176BB38} (2021-12-03 07:22:27) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Refer to suggestive list mentioned in notes tab
Note on D8: ====== ID#AAAARN0BJ_A tc={EACC9A72-0229-45C4-92AC-E9DFD7FF57CE} (2021-12-03 07:22:27) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Refer to suggestive list mentioned in notes tab

## Notes
S No. | Indicative Procurement Category | Results Area
1 | Goods | RA 1
2 | Services | RA 2
3 | Misc (Please Specify) | RA 4
Use of GEM
Yes
No
Name/Description of Procurement/Selection
Details of category eg. Furniture, equipment, etc.
Market Approach
National
International