## State (SPIU + SMAC) (2)
FORMAT FOR SUBMISSION OF PROCUREMENT DETAILS [STRIVE]
State: Uttarakhand
Sl. No. | Full Name of Procuring Entity (SPIU/ ITI/ SMAC/ IC) | Prourement Training Received Before Initiating Procurement [Yes/No] | If Column C is Yes, kindly provide the below details |  |  | Procurement Complaint Protocol Available in Public Domain [Yes/No] | If Yes, Kindly Provide details/URL, etc. | Prepared Procurement Plan [Yes/No] | Applicable Procurement Rules | Disclosed Procurement Plan in Public Domain [Yes/No] | If Yes, Kindly Povide Details of Publication of Procurement Plan, including URL | Procurement Package Number | Procurement Category [Goods/Work/Consultancy/Non-Consulting Services] | Estimated Cost [INR] | Eprocurement [EPROC] or Manual Procurement [MPROC] | If EPROC, Kindly provide URL | Market Approach [National/International] | Open Tender/Quotations/GEM/Direct Contract | Tender Floating Date/Invitation sent | Justification for Direct Selection, if done | Supplier/ Contractor Name with City | *Eligible as per STRIVE Program | LOA/ Contract Date | Contract Amount [INR] | Contract Amount [Eq US$] [1 US$=INR75] | Contract Completion Date | Contract Awards details disclosed (Y/N) | If Yes, Kindly Provide details/URL, etc. | Status on Date [% Physical Progress and % Financial Progress] | Complaint recd, if any [Yes/No] | Remarks
|  |  | who received | who provided | number trained
1 | SPIU Strive Uttarakhand | No |  |  |  | Yes | https://dsde.uk.gov.in/?page_id=1351 | Yes | Sate Procurement Rule 2017 | Yes | https://dsde.uk.gov.in/?page_id=1351 |  | Non-Consultancy Service | 48,06,928.00 | MPROC |  | National | Direct Contract |  |  |  | Yes |  | 4806928 | 64092.3733 | 2021-03-01 | Yes |  |  | No | ITDA is State govt. Authorised Agency for SWAN
2 | SPIU Strive Uttarakhand | No |  |  |  | Yes | https://dsde.uk.gov.in/?page_id=1352 | Yes | Sate Procurement Rule 2018 | Yes | https://dsde.uk.gov.in/?page_id=1352 |  | Non-Consultancy Service | 71,93,072.00 | MPROC |  | National | Direct Contract |  |  |  | Yes |  | 7193072 | 95907.6267 | 2022-03-26 | No |  |  | No
3 | SPIU Strive Uttarakhand | No |  |  |  | Yes | https://dsde.uk.gov.in/?page_id=1353 | Yes | Sate Procurement Rule 2019 | Yes | https://dsde.uk.gov.in/?page_id=1353 |  | Goods | 25,00,000.00 |  |  | National | GEM |  |  |  | Yes |  | 2500000 | 33333.3333 | 2022-03-29 | No |  |  | No
4 | SPIU Strive Uttarakhand | No |  |  |  | Yes | https://dsde.uk.gov.in/?page_id=1354 | Yes | Sate Procurement Rule 2020 | Yes | https://dsde.uk.gov.in/?page_id=1354 |  | Civil work | 70,00,000.00 |  |  | National | Direct Contract |  |  |  | Yes |  | 6667000 | 88893.3333 | 2022-06-15 | No |  |  | No
5 | SPIU Strive Uttarakhand | No |  |  |  | Yes | https://dsde.uk.gov.in/?page_id=1355 | Yes | Sate Procurement Rule 2021 | Yes | https://dsde.uk.gov.in/?page_id=1355 |  | Equipment | 50,00,000.00 |  |  | National | GEM |  |  |  | Yes |  | 5000000 | 66666.6667 | 2022-03-05 | No |  |  | No
6 | SPIU Strive Uttarakhand | No |  |  |  | Yes | https://dsde.uk.gov.in/?page_id=1356 | Yes | Sate Procurement Rule 2022 | Yes | https://dsde.uk.gov.in/?page_id=1356 |  | Non-Consultancy Service | 4400000 |  |  | National | Open Tender |  |  |  | Yes |  | 4400000 | 58666.6667 | 2022-07-14 | No |  |  | No
7 | SPIU Strive Uttarakhand | No |  |  |  | Yes | https://dsde.uk.gov.in/?page_id=1357 | Yes | Sate Procurement Rule 2023 | Yes | https://dsde.uk.gov.in/?page_id=1357 |  | Consultancy Service | 250000 | MPROC |  | National | Quotations |  |  |  | Yes |  | 250000 | 3333.3333 | 2022-03-31 | No |  |  | No
8 | SPIU Strive Uttarakhand | No |  |  |  | Yes | https://dsde.uk.gov.in/?page_id=1358 | Yes | Sate Procurement Rule 2024 | Yes | https://dsde.uk.gov.in/?page_id=1358 | [13 empty] | 0
9 | [24 empty] | 0
10 | [24 empty] | 0
11 | [24 empty] | 0
12 | [24 empty] | 0
13 | [24 empty] | 0
NOTE 1 | For Column V titled '*Eligible as per STRIVE Program [Y/N]' : Firms on Bank's list of Ineligible Firms and Individuals are not eligible for award of Contract under STRIVE
NOTE 2 | Please confirm thresholds of procurement as per Para 4.2.1 on Page 104 of Operational Manual have been adhered to. In case of exception kindly provide details of exceptions in the table below :
FORMAT FOR SUBMISSION OF PROCUREMENT DETAILS [STRIVE] FOR EXCEPTIONS AS AT NOTE 2
Sl. No. | Full Name of Procuring Entity (SPIU/ ITI/ SMAC/ IC) | Prourement Training Received Before Initiating Procurement [Yes/No] | If Column C is Yes, kindly provide the below details |  |  | Procurement Complaint Protocol Available in Public Domain [Yes/No] | If Yes, Kindly Provide details/URL, etc. | Prepared Procurement Plan [Yes/No] | Applicable Procurement Rules | Disclosed Procurement Plan in Public Domain [Yes/No] | If Yes, Kindly Povide Details of Publication of Procurement Plan, including URL | Procurement Package Number | Procurement Category [Goods/Work/Consultancy/Non-Consulting Services] | Estimated Cost [INR] | Eprocurement [EPROC] or Manual Procurement [MPROC] | If EPROC, Kindly provide URL | Market Approach [National/International] | Open Tender/Quotations/GEM/Direct Contract | Tender Floating Date/Invitation sent | Justification for Direct Selection, if done | Supplier/ Contractor Name with City | *Eligible as per STRIVE Program | LOA/ Contract Date | Contract Amount [INR] | Contract Amount [Eq US$] [1 US$=INR75] | Contract Completion Date | Contract Awards details disclosed (Y/N) | If Yes, Kindly Provide details/URL, etc. | Status on Date [% Physical Progress and % Financial Progress] | Complaint recd, if any [Yes/No] | Remarks
|  |  | who received | who provided | number trained
1 | [24 empty] | 0
2
3
4
5
6
7
8
9
10 | [24 empty] | 0

## ITIs
FORMAT FOR SUBMISSION OF PROCUREMENT DETAILS [STRIVE]
State:
Sl. No. | Full Name of Procuring Entity (SPIU/ ITI/ SMAC/ IC) | Prourement Training Received Before Initiating Procurement [Yes/No] | If Column C is Yes, kindly provide the below details |  |  | Procurement Complaint Protocol Available in Public Domain [Yes/No] | If Yes, Kindly Provide details/URL, etc. | Prepared Procurement Plan [Yes/No] | Applicable Procurement Rules | Disclosed Procurement Plan in Public Domain [Yes/No] | If Yes, Kindly Povide Details of Publication of Procurement Plan, including URL | Procurement Package Number | Procurement Category [Goods/Work/Consultancy/Non-Consulting Services] | Estimated Cost [INR] | Eprocurement [EPROC] or Manual Procurement [MPROC] | If EPROC, Kindly provide URL | Market Approach [National/International] | Open Tender/Quotations/GEM/ Direct Contract | Tender Floating Date/Invitation sent | Justification for Direct Selection, if done | Supplier/ Contractor Name with City | *Eligible as per STRIVE Program | LOA/ Contract Date | Contract Amount [INR] | Contract Amount [Eq US$] [1 US$=INR75] | Contract Completion Date | Contract Awards details disclosed (Y/N) | If Yes, Kindly Provide details/URL, etc. | Status on Date [% Physical Progress and % Financial Progress] | Complaint recd, if any [Yes/No] | Remarks
|  |  | who received | who provided | number trained
1 | [24 empty] | 0
2 | [24 empty] | 0
3 | [24 empty] | 0
4 | [24 empty] | 0
5 | [24 empty] | 0
6 | [24 empty] | 0
7 | [24 empty] | 0
8 | [24 empty] | 0
9 | [24 empty] | 0
10 | [24 empty] | 0
11 | [24 empty] | 0
12 | [24 empty] | 0
13 | [24 empty] | 0
NOTE 1 | For Column V titled '*Eligible as per STRIVE Program [Y/N]' : Firms on Bank's list of Ineligible Firms and Individuals are not eligible for award of Contract under STRIVE
NOTE 2 | Please confirm thresholds of procurement as per Para 4.2.1 on Page 104 of Operational Manual have been adhered to. In case of exception kindly provide details of exceptions in the table below :
FORMAT FOR SUBMISSION OF PROCUREMENT DETAILS [STRIVE] FOR EXCEPTIONS AS AT NOTE 2
Sl. No. | Full Name of Procuring Entity (SPIU/ ITI/ SMAC/ IC) | Prourement Training Received Before Initiating Procurement [Yes/No] | If Column C is Yes, kindly provide the below details |  |  | Procurement Complaint Protocol Available in Public Domain [Yes/No] | If Yes, Kindly Provide details/URL, etc. | Prepared Procurement Plan [Yes/No] | Applicable Procurement Rules | Disclosed Procurement Plan in Public Domain [Yes/No] | If Yes, Kindly Povide Details of Publication of Procurement Plan, including URL | Procurement Package Number | Procurement Category [Goods/Work/Consultancy/Non-Consulting Services] | Estimated Cost [INR] | Eprocurement [EPROC] or Manual Procurement [MPROC] | If EPROC, Kindly provide URL | Market Approach [National/International] | Open Tender/Quotations/GEM/Direct Contract | Tender Floating Date/Invitation sent | Justification for Direct Selection, if done | Supplier/ Contractor Name with City | *Eligible as per STRIVE Program | LOA/ Contract Date | Contract Amount [INR] | Contract Amount [Eq US$] [1 US$=INR75] | Contract Completion Date | Contract Awards details disclosed (Y/N) | If Yes, Kindly Provide details/URL, etc. | Status on Date [% Physical Progress and % Financial Progress] | Complaint recd, if any [Yes/No] | Remarks
|  |  | who received | who provided | number trained
1 | [24 empty] | 0
2 | [24 empty] | 0
3 | [24 empty] | 0
4 | [24 empty] | 0
5 | [24 empty] | 0
6 | [24 empty] | 0
7 | [24 empty] | 0
8 | [24 empty] | 0

## Notes (hidden)
S No. | Eligible Expenditure
1 | Yes
2 | No
S No. | Indicative Procurement Category
1 | Civil work
2 | Computer
3 | Equipment
4 | Furniture
5 | Tools
6 | Books and Periodicals
7 | Training
8 | Goods
9 | Consultancy Service
10 | Non-Consultancy Service
11 | Misc (Please Specify)
S No. | Market Approach
1 | Open Tender
2 | Quotations
3 | GEM
4 | Direct Contract
S No. | Market Approach
1 | National
2 | International
S No. | Manual/ Online Method
1 | EPROC
2 | MPROC