## Procurement Datasheet Annex 1
Annexure-1 : Only SPIU details to be filled in this file
State Procurement Activities Data Sheet under STRIVE
Table 1: Contracts awarded under the Program component :
(Enter dates for EOI issuance and Contract Effectiveness. This will help to identify any delays in the procurement cycle and address the challenges.)
S.No. | Name of Procuring Entity | Results Area of Program | Description of Contract | Method of Procurement/Selection | Date of EOI/IFB Issuance | Date of Contract Signature | Date of Contract Effectiveness | Value of Contract [INR]
1 | SPIU Uttarakhand | RA 2 | Internet connectivity through SWAN in 05 ITIs | Through State Govt. approved agencey ITDA Dehradun |  | 18-03-2021 | 31-03-2021 | 48,06,928.00
2 | SPIU Uttarakhand | RA 2 | Website designing | Quotation |  | 13-07-2020 | 13-07-2020 | 2,50,000.00
3
4
Table 2: Status of items presently under procurement for the Program component (If any)
(Enter all dates that are applicable)
S.No. | Name of Procuring Entity | Results Area of Program | Description of Procurement | Method of Procurement/Selection | Estimated Cost [INR] | Date of EOI/IFB Issuance | Date of RFP issuance | Date of technical proposal opening | Date of financial proposal opening | Date of contract award decision | Duration of Contract [Months]
1 | SPIU Uttarakhand | RA 2 | Civil Maintance work of Hostel in 04 Govt it is | Through State Govt. approved agencey | 70,00,000.00
2 | SPIU Uttarakhand | RA 2 | Smart classroom in 24 Govt ITI | E- Procurement/ GeM | 50,00,000.00
3 | SPIU Uttarakhand | RA 2 | Tracer study | E- Procurement | 4400000
4
5
Table 3: Implementing agency (IA) wise status update regarding publishing of procurement plans (PP) along with URL of the web page where it is published.
S.No. | Name of Procuring Entity | Results Area of Program | PP published? (Yes/ No) | URL of published PP | CAN Published [Yes/No] | URL of published CAN
1 | SPIU Uttarakhand | RA 2 | Yes | https://dsde.uk.gov.in/?page_id=1351 | Yes | https://dsde.uk.gov.in/?page_id=1351
2
3
NOTE 1 : | Firms on Bank's list of Ineligible Firms and Individuals are not eligible for award of Contract under STRIVE
NOTE 2: | The program excludes procurement activities above a certain threshold specified in Para 4.2.1 on Page 104 of the Operations Manual

## Sheet1 (hidden)
Results Area of Program
RA 1
RA 2
RA 4
Yes
No